

Chief Executive Officer

Richard Evans OBE

**CRAG Work Plan October 2021 – September 2022**

**TARGETS FOR October 2021-Septemeber 2022:**

**Action planner**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Action** | **Objectives**  **(SMART goals)** | **Responsible members** | **Target date** | **Status / update** |
| 1 | To provide advice and information relating to the continuing education and professional development needs of advanced/consultant practitioners | * Publishing the revised guidance for the Support of New and Established consultant radiographer roles * Organising quarterly CRAG virtual drop in Q&A session and annual study day with wider advanced/consultant practitioners’ network * Update CRAG webpages | SC, LD and NR leading subgroup.  LD, RM, RB and CF  All to contribute | April 2022  July 2022  September 2022 | Facilitate via online teams.  Update webpages with new information (first update completed Feb 22 TOR). |
| 2 | To act as a source of expertise and leadership to SoR on future strategies of facilitating radiographers to extend their scope of practice as advanced/consultant practitioners | * Engaging with all current SoR advisory groups/ responsible professional officers as appropriate * CRAG recorded virtual webinars on career progression for students * Representing the SoR vision and values on advanced/consultant practice in radiography when engaging with external stakeholders | Chair and Deputy Chair  NB, LF, LS, RB.  All | April 2022  April 2022  September 2022 | ToR raised at the officers meeting agenda October 2021  ToR has spoken with the SoR officer for students – there is a series of webinars for students commencing spring/summer 2022 – CRAG session noted as possible for spring. |
| 3 | To collaborate with the SoR Research Advisory group on facilitating radiographer-led research | * Explore the provision of possible virtual research webinars showcasing research work by advanced/consultant practitioners * Identifying joint projects between advisory groups to enhance research domains of advanced/consultant practitioners. | Chair and Deputy Chair  Chair and Deputy Chair | September 2022  September 2022 |  |
| 4 | To provide professional advice and support to CoR in formulating professional and educational standards of advanced/consultant practitioners | * CRAG acting as a pioneering expert group to validate the new consultant practitioner accreditation system * Involving in designing bespoke assessor training package for advanced/consultant practitioner accreditation * Collegiate work with diagnostic and therapeutic radiography service managers to raise awareness of’professional and educational standards required to fulfil the roles of advanced/consultant practitioners. | HY, LF, KN, VM, CF and SW  BS, SC and NR  Chair and Deputy Chair | April 2022  April 2022  April 2022 | ToR contacted the officers for education and accreditation – they will be in touch when the new accreditation software is working and launched.  Officers for education and accreditation are aware.  ToR has spoken to AL, the officer who supports service managers – arranged a meeting to chat about collaboration. Positive with possible inclusion on managers study day agenda. |