Chief Executive Officer

Richard Evans OBE

Radiographic Informatics Advisory Group Work Plan 2021 – 2022

OBJECTIVES:

TARGETS FOR 2021-2022:

Action planner

|  | Action | Objectives (SMART goals) | Responsible members | Notes (may include anticipated benefits, costs, external advisors) | Target date | Status / update |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | SoR member engagement | Review and update SoR radiographic informatics webpages. Review and update RIG member profiles. | Anant Tracy | SoR have employed a digital content executive to oversee web content (Blu Evans). He is available to update pages and advise re design etc. Blu has updated the radiographic informatics advisory group page with updated bios. |  | Anant & Blu introductory email. Completed |
|  |  | Complete December 2021 / January 2022 articles for synergy news. Provide a 2022 article in Synergy News | Alex All | Radiographic Informatics Advisory Group (RIG); June 2022; Wednesday 10 May 2022; Tracy O’Regan: TracyO@sor.org. Overview of group work and members. | May 2022 | Completed Completed |
|  |  | Continue to answer members questions. Develop Q&A section for SoR informatics webpage. | Alex |  |  | Pending |
| 2 | Support the development of professional and educational standards | Share group knowledge and best practice; review current SoR informatics guidance and update, signpost to training, publications, competency frameworks etc. | All | SoR webpages available for signposting. |  | Ongoing |
|  |  | Provide group feedback, critique, and comments to consultations. | All | Signposting to consultations and call for responses via informatics advisory group synapse page. |  | Ongoing |
|  |  | Thematic review of member questions (received 2021). Overview of themes to SoR EDPP (Charlotte), plan to develop any necessary guidance. | Coordinate via synapse after January completion of articles. | Alex has access to questions. |  | Ongoing |
| 3 | Engage with stakeholders and patient groups | SoR informatics advisory group to be regarded as a reliable source of information and advice. Progress partnerships and explore joint working with relevant SoR groups, external informatics groups, arms-length bodies, charities etc. | Chair and vice chair. |  |  | Ongoing |
| 4 | Ensure a safe place to work for members | Advice to council and members with respect to current healthcare focus in informatics, for example, regulation, procurement, project implementation. | All members | SoR consultations posted on synapse. Val updates synapse with requests from council/SoR senior leadership team. |  | Ongoing |
| 5 | Influence the future delivery of radiographic informatics | Explore current workforce guidance and publications for radiographic informatics professionals. Consider to update or provide new guidance if necessary. | All members | Example guidance for clinical academic careers: Clinical-Academic-Radiographer-Guidance-for-the-support-of-new-and-established-roles-Final (sor.org) Example ‘the role of the radiographer in’: the_role_of_the_radiographer_in_dxa_and_osteoporosis_services_-_final_proof.pdf_2 (sor.org) |  | Ongoing |